# UNITED NATIONS CHILDREN'S FUND

# Terms of Reference

# PMER Sindh Office

1. Programme information : Planning, Monitoring, Evaluation and Reporting Programme (No. & Name) : Planning Monitoring and Evaluation, Sindh Project (No. & Name) : IR 1.2 : Multiple Indicator Cluster Survey

2. Purpose of Assignment: The Multiple Indicator Cluster Survey (MICS) is an international household survey programme developed by UNICEF. MICS is designed to collect statistically sound, internationally comparable estimates of key indicators that are used to assess the situation of children and women in the areas of health, education, child protection and HIV/AIDS. MICS also provides data that is essential for developing evidence-based policies as well as monitor progress towards national goals and global commitments aimed at promoting the welfare of children, including the Millennium Development Goals (MDGs). Since 1995, UNICEF has supported the implementation of MICS, assisting countries in generating high quality data on the situation of children and women. Over the last 17 years and four rounds of MICS, 240 MICS surveys have been conducted in more than 100 countries. The data generated from MICS5 and other nationally representative household surveys will be critically important for final MDG reporting, Monitoring Results for Equity Systems (MoRES), and for monitoring commitments made toward A Promise Renewed. The Sindh Bureau of Statistics (BOS) participated in the first round of MICS in year 2003-4. In 2013, the Government of Sindh, Bureau of Statistics commenced implementation of the second round of MICS (MICS5) with the technical support of UNICEF. The data collection started in February 2014 and was completed in August 2014. The Key Findings Report has been finalized and will be launched shortly. With the reporting of MDG due in 2015, UNICEF would like to expedite the process of producing final report for Sindh MICS. Hence, the draft report has already been compiled. UNICEF Sindh Office now requires the support of a consultant to review the draft write-up and produce a final MICS report in line with the Global MICS Reporting Standards.

3. Duty station: Offsite with possible visit to Karachi if considered necessary following the first phase of work, to be determined at the start of the consultancy.

4. Supervisor: PMER UNICEF, Karachi

5. Major tasks to be accomplished: Review draft report developed by Sindh MICS team and in consultation with BoS and UNICEF Sindh, rewrite significant sections of each chapter in line with the feedback and advice provided by the UNICEF Regional Office (RO) to produce a clean draft which will be shared with line departments and other stakeholders for their inputs and shared with Regional Office for second review. Following a 2 week period, incorporate revisions and changes required as suggested by all stakeholders. Ensure document is fully edited and proof read for final submission to the RO/UNICEF Headquarters team. Following a 2 week period, based on feedback from RO/HQ make any final revisions to the report. During the above mentioned stages/activities, support and guidance will be provided by the PMER Specialist UNICEF Sindh, MICS Coordinator at CO, Survey Coordinator from Bureau of Statistics, Planning and Development Department, Regional Office and Global MICS team.

Deliverables: MICS Final Report (based on MICS5 global standards template for report writing).

Time Duration The estimated duration of the contract is 28 working days spread over 3 months from the period of April to June 2015. Phase 1: 20 working days to rewrite report Phase 2: 5 working days to make changes based on review from stakeholders and ROSA Phase 3: 3 working days for final changes after final review from HQ/RO There will be a gap of 2 weeks in between each phase

Qualifications or specialized knowledge/experience required: Education: Advanced university degree in Demography, Statistics, Epidemiology, Public Health or any other Social Sciences related technical field Work Experience: At least seven years’ experience in writing statistical reports (report writing using MICS or Demographic and Health Survey (DHS) template is essential). Special skills: expertise in statistical analyses (and data interpretation highly desirable. Excellent oral and written communications in English. Excellent data analysis and interpretation skills. Excellent communication and interpersonal skills. Knowledge of UNICEF programmatic priorities (health, education, nutrition, water & sanitation, child protection) etc. preferable. The consultant should respect the confidentiality of the MICS data as well as any country specific MICS documents that will be produced throughout the MICS process. The consultant can use the documents only for the tasks related to these terms of reference. Consultant(s) will provide own stationery and materials (computer, discs, software) All payments must be within the contract agreement paid against deliverables No contract will commence unless the contract is signed by both UNICEF and the consultant(s) The consultant is expected to work independently with minimum supervision.

If you are qualified and interested in the position, please forward your application with updated UN Personal History Form (Available at www.unicef.org/employ), with the title of the position in the subject line, via email to sjilani@unicef.org, and by March 21st, 2015. Please indicate your ability, availability and daily rate to undertake the terms of reference above. Applications submitted without a daily/monthly rate will not be considered.